## Sheet1
Tasklist
Task Number | Task | Sub Task
1 | Data MOAT | Get mock data from Trace3
IF mock data not available use a LLM to generate the same
Write backend functions to serialize data received and store them
2 | Frontend | Initial Skeleton and ReactJS Framework
Create all routes for the web application
Beautify with static components and charts from open source react component libraries like shadCN, magicUI
Link the frontend with the backend
Proceed to testing
3 | Backend | Initialize the Django Skeleton and Django Rest Framework
Create models for the system and migrate them
Create REST API endpoints using the models
Link the frontend with backend
Proceed to testing
4 | Testing | Test endpoint with raw data using postman, create and save a postman collection for documentation for Trace3
Test the backend for security protocols
Test the frontend for bugs / view issues on multiple differnet devices and systems
Complete testing
5 | Packaging | For deploymenet, ask trace3 what they prefer, if they want the whole application to be served via a docker image
Deploy on a cloud hosting provider - frontend on a static app service, and backend via Kubernetes / a normal VM

## Sheet2
Sr. No. | Sprint | Task Name | Sub-task Name | Task Status | Primary Assignee | Start Date | Actual Start Date | End Date | Actual End Date | Issues / Blockers / Comments / Description